## Blad1
QuickMath | User story # | Work item # | 16-05 - Remaining Hours | 17-05 Remaining Hours | 18-05 Remaining Hours | 21-05 Remaining Hours
Sprint 1 | User story 1 | Work item 1 | 1 | 1 | 0.5 | 0
| User story 2 | Work item 2 | 1 | 1 | 0.5 | 0
|  | Ideal | 2 | 1.3333 | 0.6667 | 0
|  | Actual | 2 | 2 | 1 | 0