## Blad1
QuickMath | User story # | Work item # | 05-06 - Remaining Hours | 06-06 Remaining Hours | 07-06 Remaining Hours | 08-06 Remaining Hours
Sprint 2 | User story 7 | Work item 7 | 4 | 1 | 0 | 0
| User story 8 | Work item 8 | 4 | 3 | 2 | 0
| User story 9 | Work item 9 | 2 | 0 | 0 | 0
| User story 13 | Work item 13 | 3 | 0 | 0 | 0
|  | Ideal | 13 | 8.6666 | 4.3333 | 0
|  | Actual | 13 | 4 | 2 | 0