## Blad1
QuickMath | User story # | Work item # | 12-06 - Remaining Hours | 13-06 Remaining Hours | 14-06 Remaining Hours | 25-06 Remaining Hours
Sprint 3 | User story 1 | Work item 2 | 3 | 2 | 0 | 0
| User story 5 | Work item 5 | 5 | 5 | 4 | 0
| User story 11 | Work item 11 | 0.5 | 0 | 0 | 0
| User story 15 | Work item 15 | 0.5 | 0.5 | 0.5 | 0
|  | Ideal | 9 | 6 | 3 | 0
|  | Actual | 9 | 7.5 | 4.5 | 0